## Audited_Tracker
Task ID | Phase | Task | Owner | Planned Start | Planned End | Actual End | Status | Progress % | Priority | Dependency | Risk Level | Planned Hours | Actual Hours | Notes | Flag_Regla1_AtrasoActivo | Flag_Regla2_DesviacionHistorica | Flag_Regla4_CalidadDatos | Flag_Regla5_CriticasSinIniciar | Flag_Regla3_BloqueoDependencia | Requiere_Atencion | Dias_Desviacion
T001 | Initiation | Project kickoff and scope confirmation | Ana PM | 2026-07-20 | 2026-07-21 | 2026-07-21 | Completed | 100 | High | - | Low | 8 | 8 | Scope approved | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 0
T002 | Initiation | Stakeholder map and RACI | Ana PM | 2026-07-21 | 2026-07-24 | 2026-07-25 | Completed | 100 | High | T001 | Low | 12 | 14 | One-day delay | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | 1
T003 | Initiation | Initial requirements workshop | Luis BA | 2026-07-22 | 2026-07-29 | 2026-07-29 | Completed | 100 | High | T001 | Low | 24 | 26 | All key stakeholders attended | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 0
T004 | Planning | Detailed project plan | Ana PM | 2026-07-27 | 2026-07-31 | 2026-08-03 | Completed | 100 | High | T002,T003 | Medium | 20 | 28 | Dependent on final requirements | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | 3
T005 | Planning | Data migration strategy | Carlos Data | 2026-07-30 | 2026-08-07 | 2026-08-10 | Completed | 100 | High | T003 | Medium | 28 | 34 | Legacy data quality issues | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | 3
T006 | Design | UX process map | Marta UX | 2026-08-03 | 2026-08-10 | 2026-08-12 | Completed | 100 | Medium | T003 | Medium | 24 | 31 | Two review cycles | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | 2
T007 | Design | Target solution architecture | Diego Tech | 2026-08-03 | 2026-08-12 | 2026-08-14 | Completed | 100 | High | T003 | High | 36 | 44 | Security review added | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | 2
T008 | Design | Security requirements definition | Sara Security | 2026-08-06 | 2026-08-14 | 2026-08-17 | Completed | 100 | High | T007 | High | 24 | 30 | External review delayed | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | 3
T009 | Build | Development sprint 1 | Diego Tech | 2026-08-17 | 2026-08-28 | 2026-09-02 | Completed | 100 | High | T006,T007 | Medium | 80 | 96 | Environment instability | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | 5
T010 | Build | API integration - payments | Diego Tech | 2026-08-24 | 2026-09-04 |  | In Progress | 75 | High | T007 | High | 72 | 68 | Third-party API intermittency | TRUE | FALSE | FALSE | FALSE | FALSE | TRUE | 0
T011 | Build | Customer notification workflow | Marta UX | 2026-08-24 | 2026-09-03 | 2026-09-04 | Completed | 100 | Medium | T006 | Low | 32 | 35 | Minor rework | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | 1
T012 | Build | Data migration rehearsal | Carlos Data | 2026-08-31 | 2026-09-09 |  | In Progress | 60 | High | T005,T009 | High | 56 | 62 | 18% records need remediation | TRUE | FALSE | FALSE | FALSE | FALSE | TRUE | 0
T013 | Build | Development sprint 2 | Diego Tech | 2026-09-01 | 2026-09-15 |  | In Progress | 45 | High | T009 | Medium | 96 | 58 | Capacity reduced by API issues | TRUE | FALSE | FALSE | FALSE | FALSE | TRUE | 0
T014 | Build | Accessibility fixes | Marta UX | 2026-09-07 | 2026-09-11 | 2026-09-14 | In Progress | 80 | Medium | T011 | Low | 20 | 16 | Awaiting final review | TRUE | FALSE | TRUE | FALSE | FALSE | TRUE | 0
T015 | Testing | Test plan and cases | Luis BA | 2026-09-07 | 2026-09-11 | 2026-09-12 | Completed | 100 | High | T009 | Low | 28 | 30 | Ready for UAT | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | 1
T016 | Testing | System integration testing (SIT) | Luis BA | 2026-09-14 | 2026-09-25 |  | Not Started | 0 | High | T010,T012,T013 | High | 72 | 0 | Blocked by build/data dependencies | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | 0
T017 | Testing | User acceptance testing (UAT) | Business Team | 2026-09-28 | 2026-10-06 |  | Not Started | 0 | High | T016 | High | 64 | 0 | Business users booked | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | 0
T018 | Testing | Defect triage and resolution | Diego Tech | 2026-09-29 | 2026-10-09 |  | Not Started | 0 | High | T016 | High | 80 | 0 | Capacity concern | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | 0
T019 | Deployment | Production readiness checklist | Ana PM | 2026-10-05 | 2026-10-09 |  | Not Started | 0 | High | T017,T018 | Medium | 24 | 0 | Checklist drafted | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | 0
T020 | Deployment | Go-live rehearsal | Diego Tech | 2026-10-12 | 2026-10-13 |  | Not Started | 0 | High | T019 | Medium | 16 | 0 | Environment to confirm | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | 0
T021 | Deployment | Production deployment | Diego Tech | 2026-10-19 | 2026-10-20 |  | Not Started | 0 | Critical | T020 | High | 20 | 0 | Go-live window reserved | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | 0
T022 | Hypercare | Hypercare support | Support Team | 2026-10-21 | 2026-10-30 |  | Not Started | 0 | High | T021 | Medium | 80 | 0 | Staffing not fully confirmed | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | 0
T023 | Closure | Post-implementation review | Ana PM | 2026-11-02 | 2026-11-04 |  | Not Started | 0 | Medium | T022 | Low | 16 | 0 | Success criteria drafted | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | 0
T024 | Closure | Benefits realization baseline | Luis BA | 2026-11-02 | 2026-11-06 |  | Not Started | 0 | Medium | T021 | Low | 20 | 0 | KPIs identified | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | 0
T025 | Closure | Final project report | Ana PM | 2026-11-05 | 2026-11-09 |  | Not Started | 0 | Medium | T023,T024 | Low | 16 | 0 | Template ready | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | 0
T026 | Initiation | Governance cadence setup | Ana PM | 2026-07-23 | 2026-07-27 | 2026-07-27 | Completed | 100 | Medium | T001 | Low | 12 | 12 | Weekly status cadence | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 0
T027 | Planning | KPI baseline definition | Luis BA | 2026-07-28 | 2026-08-04 | 2026-08-06 | Completed | 100 | High | T003 | Medium | 20 | 24 | Source data inconsistent | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | 2
T028 | Build | Legacy data remediation | Carlos Data | 2026-08-24 | 2026-09-16 |  | In Progress | 40 | Critical | T005 | High | 64 | 54 | Could delay migration | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 0
T029 | Testing | Security penetration test | Sara Security | 2026-09-16 | 2026-09-23 |  | Not Started | 0 | Critical | T008,T013 | High | 32 | 0 | Vendor date not confirmed | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | 0
T030 | Deployment | Training materials and enablement | Marta UX | 2026-09-21 | 2026-10-02 |  | Not Started | 0 | Medium | T014,T015 | Medium | 40 | 0 | Content in draft | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | 0

## Meeting_Notes
Meeting Date | Meeting | Participants | Key Updates | Decisions | Actions / Owner | Due Date | Potential Risk
2026-08-28 | Weekly Project Status | PM; BA; Tech; Data | SIT preparation started. API integration remains unstable. | Prioritize payment API remediation before non-critical features. | Diego: escalate API vendor issue; Carlos: provide remediation plan | 2026-09-02 | Schedule impact
2026-09-04 | Data Migration Review | PM; Data; BA | 18% of legacy records fail validation rules. | Run additional remediation cycle before migration rehearsal. | Carlos: remediation backlog; Luis: update validation rules | 2026-09-09 | Migration delay
2026-09-08 | Leadership Check-in | Sponsor; PM; BA | Project still targets Oct 20 go-live, but dependencies are tightening. | Escalate any critical dependency that threatens SIT start. | Ana: dependency review with sponsor | 2026-09-11 | Go-live risk
2026-09-10 | Security Coordination | Security; Tech; PM | Penetration test vendor has not confirmed date. | Hold provisional slot for Sep 16-23 and confirm within 48 hours. | Sara: confirm vendor; Diego: prepare environment | 2026-09-14 | Testing blocker
2026-09-11 | Weekly Project Status | PM; BA; Tech; UX | SIT is scheduled for Sep 14 and depends on API, migration rehearsal, and Sprint 2. | Create a dependency-focused recovery plan. | Ana: recovery plan; Diego: API recovery options; Carlos: migration status | 2026-09-14 | Critical path compression